## ProductBacklog
User Story | Scrum Points | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Priority | Status
As an admin, I want to be able to add employees so that customers have a wide option of services. | 1 | 1 | 2 |  |  |  | high
As an admin I want to be able to edit data on employees (working hours for the next month) so that I can ensure customers have the up to date information of when an employee is available. | 5 |  | 2 |  |  |  | medium |  | Key | Satus | Priority
As an admin I want to be to look at the history of an employee's booking, so that I can see when a customer last had a booking | 1 | 1 | 2 |  |  |  | low |  |  | Not Started | High
As an admin I want to be able to see new bookings so that I can ensure there are no conflicts with other bookings. | 2 | [8 empty] | In Progress | Medium
As an admin I want to be able to see the availability of an employee over the next week to ensure that customers can get the services we provide | 2 | [8 empty] | Completed | Low
As a customer I want to be able to see what bookings are available for a service so that I can see what time will best suit me. | 3 | 1 |  |  |  |  | high
#N/A
As a customer I want to see a list of available services so that I can choose the best service for my needs. | 1 | 1 |  |  |  |  | low
As a business owner, I want to have my own account, so that I can delegate tasks and change settings. | 2 |  | 2 |  |  |  | low |  | People
As a worker, I want to have a worker account, So that I can login in AND see my dashboard for the daily job requirements. | 2 | 1 | 2 |  |  |  | medium |  |  | Jesse
| #N/A | [8 empty] | Hilson
As a customer, I want to know the business’ location, so that I can visit them in person | 1 | [8 empty] | Alexander
As a customer, I want to sign up with the website, so that I could be recognised by the business whenever I visit them. | 3 | 1 |  |  |  |  | high |  |  | Simon
As a customer, I want to know the business’ contact email, so that I can email them when I have an enquiry | 1 | [8 empty] | Berke
As an admin, I want to manage user privileges/account levels when they sign up, So that I can manage their functionalities | 3
#N/A
#N/A
As a customer, I want to have my own account, so that I can keep track of my booked appointment | 2
As a customer, I want to have a persistent account, so I can review my personal bookings history. | 2
As a customer, I want a personalize home page, so that I can review my bookings history. | 2 | 1 |  |  |  |  | medium
#N/A
As a customer, I want to have a detailed bookings history, so I can base future bookings on previous experiences e.g. What worker conducted the interview or what service was provided. | 1 | 1 | 2 |  |  |  | high
As a worker, I want to have a persistent account, so I can access my respective profile and information. | 2 | 0 |  |  |  |  | high
As a worker, I want to have a profile page, so I can review my working schedule. | 2
As a worker, I want to have a detailed schedule, so I can review the details of my assigned bookings. | 2
As a worker, I want to have a profile page, so I can review my current responsibilities i.e. what services I am charged with providing. | 2
As a customer I want to be able to enter/change my phone number so that I can be contacted with details or changes in my booking. | 1
As a customer I want to have a profile page so that I can view or edit details that the business has regarding to me. | 1
As a customer I want to know how long there is left until my booking so that I can cancel it if I need to. | 2
As a customer I want a persistent profile so that I don’t have to re-enter details every time I use the service. | 1
As a customer I want it to be clear that I can no longer cancel a booking so that I don’t waste time trying to click a button that does nothing | 1
As a customer I want it to be clear that I am logged in so that I can easily access my profile page. | 1 | 1 |  |  |  |  | low
As an admin I want customers to enter their name, address, phone, username, and password saved in the database, so that I could manage, fix and maintain customer details. | 1 | 1 |  |  |  |  | medium
As a customer, I want to log into the website, so that I could use the services offered by the business. | 2 | 1 |  |  |  |  | high
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A

## ScrumPoker
User Story | Hillson | Jesse | Alexander | Berke | Simon | Mode | Count | Verfided
As an admin, I want to be able to add employees so that customers have a wide option of services. | 2 | 1 | 1 | 2 | 1 | 1 | 3 | TRUE
As an admin I want to be able to edit data on employees (working hours for the next month) so that I can ensure customers have the up to date information of when an employee is available. | 2 | 2 | 2 | 2 | 2 | 2 | 5 | TRUE | Fibbonacci Sequence
As an admin I want to be to look at the history of an employee's booking, so that I can see when a customer last had a booking | 1 | 2 | 1 | 1 | 2 | 1 | 3 | TRUE | 1
As an admin I want to be able to see new bookings so that I can ensure there are no conflicts with other bookings. | 1 | 2 | 2 | 2 | 2 | 2 | 4 | TRUE | 2
As an admin I want to be able to see the availability of an employee over the next week to ensure that customers can get the services we provide | 2 | 2 | 2 | 2 | 2 | 2 | 5 | TRUE | 3
As a customer I want to be able to see what bookings are available for a service so that I can see what time will best suit me. | 3 | 2 | 3 | 2 | 3 | 3 | 3 | TRUE | 5
0 |  | 1 |  |  |  | #N/A | 0 | FALSE | 7
As a customer I want to see a list of available services so that I can choose the best service for my needs. | 1 | 1 | 1 | 1 | 1 | 1 | 5 | TRUE | 13
As a business owner, I want to have my own account, so that I can delegate tasks and change settings. | 2 | 2 | 3 | 3 | 2 | 2 | 3 | TRUE | 21
As a worker, I want to have a worker account, So that I can login in AND see my dashboard for the daily job requirements. | 2 | 2 | 2 | 2 | 2 | 2 | 5 | TRUE | 34
0 | [5 empty] | #N/A | 0 | FALSE
As a customer, I want to know the business’ location, so that I can visit them in person | 1 | 1 | 1 | 1 | 1 | 1 | 5 | TRUE
As a customer, I want to sign up with the website, so that I could be recognised by the business whenever I visit them. | 3 | 3 | 3 | 2 | 3 | 3 | 4 | TRUE
As a customer, I want to know the business’ contact email, so that I can email them when I have an enquiry | 1 | 1 | 1 | 1 | 1 | 1 | 5 | TRUE
As an admin, I want to manage user privileges/account levels when they sign up, So that I can manage their functionalities | 2 | 3 | 3 | 3 | 3 | 3 | 4 | TRUE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
As a customer, I want to have my own account, so that I can keep track of my booked appointment | 2 | 2 | 2 | 2 | 2 | 2 | 5 | TRUE
As a customer, I want to have a persistent account, so I can review my personal bookings history. | 2 | 2 | 2 | 2 | 2 | 2 | 5 | TRUE
As a customer, I want a personalize home page, so that I can review my bookings history. | 2 | 2 | 2 | 3 | 2 | 2 | 4 | TRUE
0 | [5 empty] | #N/A | 0 | FALSE
As a customer, I want to have a detailed bookings history, so I can base future bookings on previous experiences e.g. What worker conducted the interview or what service was provided. | 2 | 1 | 1 | 1 | 1 | 1 | 4 | TRUE
As a worker, I want to have a persistent account, so I can access my respective profile and information. | 1 | 2 | 2 | 2 | 2 | 2 | 4 | TRUE
As a worker, I want to have a profile page, so I can review my working schedule. | 3 | 2 | 2 | 2 | 2 | 2 | 4 | TRUE
As a worker, I want to have a detailed schedule, so I can review the details of my assigned bookings. | 2 | 3 | 2 | 2 | 3 | 2 | 3 | TRUE
As a worker, I want to have a profile page, so I can review my current responsibilities i.e. what services I am charged with providing. | 2 | 2 | 2 | 2 | 3 | 2 | 4 | TRUE
As a customer I want to be able to enter/change my phone number so that I can be contacted with details or changes in my booking. | 1 | 1 | 1 | 1 | 1 | 1 | 5 | TRUE
As a customer I want to have a profile page so that I can view or edit details that the business has regarding to me. | 1 | 1 | 1 | 1 | 1 | 1 | 5 | TRUE
As a customer I want to know how long there is left until my booking so that I can cancel it if I need to. | 2 | 2 | 1 | 1 | 2 | 2 | 3 | TRUE
As a customer I want a persistent profile so that I don’t have to re-enter details every time I use the service. | 1 | 1 | 1 | 1 | 1 | 1 | 5 | TRUE
As a customer I want it to be clear that I can no longer cancel a booking so that I don’t waste time trying to click a button that does nothing | 1 | 1 | 1 | 1 | 1 | 1 | 5 | TRUE
As a customer I want it to be clear that I am logged in so that I can easily access my profile page. | 1 | 1 | 1 | 1 | 1 | 1 | 5 | TRUE
As an admin I want customers to enter their name, address, phone, username, and password saved in the database, so that I could manage, fix and maintain customer details. | 1 | 1 | 1 | 1 | 1 | 1 | 5 | TRUE
As a customer, I want to log into the website, so that I could use the services offered by the business. | 3 | 2 | 2 | 2 | 2 | 2 | 4 | TRUE
[6 empty] | #N/A | 0 | FALSE
[6 empty] | #N/A | 0 | FALSE
[6 empty] | #N/A | 0 | FALSE
[6 empty] | #N/A | 0 | FALSE
[6 empty] | #N/A | 0 | FALSE
[6 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE
0 | [5 empty] | #N/A | 0 | FALSE

## Sprint1Burndown
User Story | Scrum Points | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
As an admin, I want to be able to add employees so that customers have a wide option of services. | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0
As an admin I want to be to look at the history of an employee's booking, so that I can see when a customer last had a booking | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0 | 0.3 | 0.2 | 0 | 0 | 0 | 0
0 | 0
0 | 0
As a customer I want to be able to see what bookings are available for a service so that I can see what time will best suit me. | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1
0 | 0
As a customer I want to see a list of available services so that I can choose the best service for my needs. | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 0 | 0.2 | 0 | 0 | 0.2 | 0.3
0 | 0
As a worker, I want to have a worker account, So that I can login in AND see my dashboard for the daily job requirements. | 2 | 0 | 0 | 0 | 0.2 | 0 | 0 | 0.3 | 0 | 0 | 1 | 0 | 0 | 0 | 0
0 | 0
0 | 0
As a customer, I want to sign up with the website, so that I could be recognised by the business whenever I visit them. | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
As a customer, I want a personalize home page, so that I can review my bookings history. | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0 | 0 | 0.8 | 0 | 0.5 | 0 | 0
0 | 0
As a customer, I want to have a detailed bookings history, so I can base future bookings on previous experiences e.g. What worker conducted the interview or what service was provided. | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
As a customer I want it to be clear that I am logged in so that I can easily access my profile page. | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0
As an admin I want customers to enter their name, address, phone, username, and password saved in the database, so that I could manage, fix and maintain customer details. | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
As a customer, I want to log into the website, so that I could use the services offered by the business. | 2 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.5 | 0.8 | 0 | 0 | 0.3 | 0 | 0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
| 18 | 0 | 0 | 0 | 0.2 | 0 | 0.2 | 3.6 | 0.8 | 0.3 | 4.2 | 0.3 | 1.5 | 2.1 | 2.3
hours left | 18 | 18 | 18 | 18 | 17.8 | 17.8 | 17.6 | 14 | 13.2 | 12.9 | 8.7 | 8.4 | 6.9 | 4.8 | 2.5
| 1.3846 | 18 | 16.6154 | 15.2308 | 13.8462 | 12.4615 | 11.0769 | 9.6923 | 8.3077 | 6.9231 | 5.5385 | 4.1538 | 2.7692 | 1.3846 | 0

## Sprint2Burndown
User Story | Scrum Points | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
As an admin, I want to be able to add employees so that customers have a wide option of services. | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0
As an admin I want to be able to edit data on employees (working hours for the next month) so that I can ensure customers have the up to date information of when an employee is available. | 5 | 0 | 0.4 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.4 | 0.4 | 0.2 | -1 | 1 | 1.6 | 1
As an admin I want to be to look at the history of an employee's booking, so that I can see when a customer last had a booking | 1 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.3 | 0 | 0 | 0 | 0.2
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
As a business owner, I want to have my own account, so that I can delegate tasks and change settings. | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
As a worker, I want to have a worker account, So that I can login in AND see my dashboard for the daily job requirements. | 2 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.1 | 0 | 0 | 0.2 | 0.4 | 0.4
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
As a customer, I want to have a detailed bookings history, so I can base future bookings on previous experiences e.g. What worker conducted the interview or what service was provided. | 1 | 0.2 | 0.2 | 0 | 0 | 0.2 | 0 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
| 12 | 0.2 | 0.7 | 0.3 | 0.3 | 0.5 | 1.8 | 0.6 | 0.8 | 1 | 1 | -1 | 1.2 | 2 | 2.6
hours left | 12 | 11.8 | 11.1 | 10.8 | 10.5 | 10 | 8.2 | 7.6 | 6.8 | 5.8 | 4.8 | 5.8 | 4.6 | 2.6 | 0
| 0.92308 | 12 | 11.0769 | 10.1538 | 9.2308 | 8.3077 | 7.3846 | 6.4615 | 5.5385 | 4.6154 | 3.6923 | 2.7692 | 1.8462 | 0.92308 | 0

## Sprint3Burndown
User Story | Scrum Points | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
hours left | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint5Burndown
User Story | Scrum Points | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
hours left | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint4Burndown
User Story | Scrum Points | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
hours left | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0